## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Subject | Description | Status ID | Status | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3657546 | 68232 | ATM Project | 29 | ATM_1-29 | 292236 | Bug | 92350 | Version 1.1 | MFT Test Case #13: Spelling mistake in output when conducting system asks customer to choose a dollar amount to withdraw function | **The function being tested:** System asks customer to choose a dollar amount to withdraw **The initial state of the system:** Menu of account types is being displayed **Steps to reproduce the defect/bug:** Insert card 1 and enter correct PIN. Select Withdrawl transaction. Choose checking account **What was the expected outcome?** System displays a menu of possible withdrawal amounts **What was the actual outcome?** System displayed a menu of possible withdrawl amounts but there is a spelling mistake in the text where it is missing $ sign. Output: Amount of cash to withdraw 1) $20 2) $40 3) 60 4) $100 5) $200 | 2 | In Progress |  |  | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 18:05 |  | 319553 | Huda Abbas | Jan. 28, 2022 19:05 | 0 | 0
3637295 | 68232 | ATM Project | 13 | ATM_1-13 | 292236 | Bug | 92349 | Version 1.0 | Balance Inquiry of Savings Account for Card 1 | **The function being tested:** Balance inquiry of the savings account for card 1 **The initial state of the system:** The system is on the menu that displays the different accounts to inquire from **Steps to reproduce the defect/bug:** Insert card 1, then enter correct PIN number. Select Balance Inquiry from the transaction types menu. **What was the expected outcome?** The expected outcome after selecting Balance Inquiry is for the new menu to display the accounts Checking and Savings since card 1 only has those accounts. It should also display the receipt of the savings account. Expected Output: Thu Jan 20 16:41:20 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 1 TRANS #2 INQUIRY FROM: SVGS TOTAL BAL: $1000.00 AVAILABLE: $1000.00 **What was the actual outcome?** It displayed Checking and Money Mart. When Money Mart is selected it displays an "Unknown Error" message with a large "$500.00" under the green menu box, The receipt of the Savings account is also displayed. Actual Output: Thu Jan 20 16:41:20 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #2 INQUIRY FROM: SVGS TOTAL BAL: $1000.00 AVAILABLE: $1000.00 | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 20, 2022 16:46 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:44 | 0 | 0 | Jan. 21, 2022 20:22 Lubaba Sheikh Defect still exists in version 1.1 | Jan. 28, 2022 17:44 Lubaba Sheikh Defect still exists in version 1.1
3657511 | 68232 | ATM Project | 21 | ATM_1-21 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #12: System asks customer to choose an account to withdraw from for Card 1 | **The function being tested:** System asks customer to choose an account to withdraw from **The initial state of the system:** Menu of transaction types is being displayed **Steps to reproduce the defect/bug:** Insert card 1 and enter correct PIN. Select Withdrawl transaction. **What was the expected outcome?** System displays a menu of account types. It should show accounts Checking and Savings only for Card 1 since it does not have a Money Market account. **What was the actual outcome?** System displayed all 3 accounts which include Checking, Savings and Money Market. | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 16:39 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:43 | 0 | 0 | Jan. 28, 2022 17:43 Lubaba Sheikh Defect still exists in version 1.1
3657529 | 68232 | ATM Project | 25 | ATM_1-25 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #17: Spelling mistake in output when conductig withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount function | **The function being tested:** A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount **The initial state of the system:** System is displaying menu of account types **Steps to reproduce the defect/bug:** Insert card 1 and enter correct PIN. Select Withdrawl transaction. Then press "Cancel" key **What was the expected outcome?** System displays an appropriate message and offers customer the option of choosing to do another transaction or not. **What was the actual outcome?** System displayed an appropriate message and offered customer to do another transaction or not, but there are spelling mistakes in the text. Output: Last transaction was cancelled Wood you like to do another transaction? 1) Yes 2) No | 3 | Resolved | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:06 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:42 | 0 | 0
3657537 | 68232 | ATM Project | 27 | ATM_1-27 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #19: System asks customer to choose an account to deposit to for Card 1 | **The function being tested:** System asks customer to choose an account to withdraw from **The initial state of the system:** Menu of transaction types is being displayed **Steps to reproduce the defect/bug:** Insert card 1 and enter correct PIN. Choose Deposit transaction. **What was the expected outcome?** System displays a menu of account types. It should show accounts Checking and Savings only for Card 1 since it does not have a Money Market account. **What was the actual outcome?** System displayed all 3 accounts which are Checking, Savings and Money Market. | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:16 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:41 | 0 | 0 | Jan. 28, 2022 17:41 Lubaba Sheikh Defect still exists in version 1.1
3657532 | 68232 | ATM Project | 26 | ATM_1-26 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #18: Spelling mistake in output when conductig a withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount function | **The function being tested:** A withdrawal transaction can be cancelled by the customer any time prior to choosing the dollar amount **The initial state of the system:** System is displaying menu of dollar amounts **Steps to reproduce the defect/bug:** Insert card 1 and enter correct PIN. Select Withdrawl transaction. Then select the Checking account. Then press "Cancel" key **What was the expected outcome?** System displays an appropriate message and offers customer the option of choosing to do another transaction or not. **What was the actual outcome?** System displayed an appropriate message and offered customer to do another transaction or not, but there are spelling mistakes in the text. Output: Last transaction was cancelled Wood you like to do another transaction? 1) Yes 2) No | 3 | Resolved | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:11 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:40 | 0 | 0
3657513 | 68232 | ATM Project | 22 | ATM_1-22 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #12: System asks customer to choose an account to withdraw from for Card 2 | **The function being tested:** System asks customer to choose an account to withdraw from **The initial state of the system:** Menu of transaction types is being displayed **Steps to reproduce the defect/bug:** Insert card 2 and enter correct PIN. Select Withdrawl transaction. **What was the expected outcome?** System displays a menu of account types. It should show accounts Checking and Money Market only for Card 2 since it does not have a Savings account. **What was the actual outcome?** System displayed all 3 accounts which include Checking, Savings and Money Market. | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 16:41 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:37 | 0 | 0 | Jan. 28, 2022 17:37 Lubaba Sheikh Defect still exists in version 1.1
3657539 | 68232 | ATM Project | 28 | ATM_1-28 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case #19: System asks customer to choose an account to deposit to for Card 2 | **The function being tested:** System asks customer to choose an account to withdraw from **The initial state of the system:** Menu of transaction types is being displayed **Steps to reproduce the defect/bug:** Insert card 2 and enter correct PIN. Choose Deposit transaction. **What was the expected outcome?** System displays a menu of account types. It should show accounts Checking and Money Market only for Card 2 since it does not have a Savings account. **What was the actual outcome?** System displayed all 3 accounts which are Checking, Savings and Money Market. | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:18 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:37 | 0 | 0 | Jan. 28, 2022 17:37 Lubaba Sheikh Defect still exists in version 1.1
3637301 | 68232 | ATM Project | 14 | ATM_1-14 | 292236 | Bug | 92349 | Version 1.0 | Balance inquiry of the Money Mart account for card 2 | **The function being tested:** Balance inquiry of the Money Mart account for card 2 **The initial state of the system:** The system is on the menu that displays the different accounts to inquire from **Steps to reproduce the defect/bug:** Insert card, then enter correct card number and PIN. Select 4 to pick Balance Inquiry from the transaction types menu. Then select Money Mart. **What was the expected outcome?** The expected outcome after selecting Money Mart is for the interface to display the correct receipt of the Money Mart account. **What was the actual outcome?** It displayed an "Invalid account type" message with no receipt shown. | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 20, 2022 16:54 |  | 319560 | Lubaba Sheikh | Jan. 28, 2022 17:32 | 0 | 0 | Jan. 28, 2022 17:32 Lubaba Sheikh Defect still exists in version 1.1
3657516 | 68232 | ATM Project | 24 | ATM_1-24 | 292236 | Bug | 92350 | Version 1.1 | MFT test case 27: Transfer function does not show correct accounts to transfer to | The function being tested is transferring money from one account to another and if the options the system displays for account transferring to are correct. **The initial state of the system ** Menu of transaction types is being displayed Steps to reproduce the defect/bug Insert a card, then enter card 1 and enter its PIN. Choose transfer as a transaction type and choose a card you want to transfer from, and you will see the window with accounts you can transfer the money to next. **What was the expected outcome? ** the expected outcome was to display checking and savings as card one only has these valid accounts associated with it. Input: choose transfer transaction The state to bring the program to: you should have the window open that displays the account you can transfer money to. Expected output: Account to transfer to 1) Checking 2) savings What was the actual outcome? Account to transfer to 1) Checking 2) savings 3) Money Market | 2 | In Progress |  |  | 319555 | Rajpreet Gill | 319555 | Rajpreet Gill | Jan. 28, 2022 16:49 |  | 319555 | Rajpreet Gill | Jan. 28, 2022 16:49 | 0 | 0
3657515 | 68232 | ATM Project | 23 | ATM_1-23 | 292236 | Bug | 92350 | Version 1.1 | MFT test case 26: Transfer function does not show correct accounts to transfer from | The function being tested is transferring money from one account to another and if the options the system displays for account transferring from are correct. **The initial state of the system ** Menu of transaction types is being displayed Steps to reproduce the defect/bug Insert a card, then enter card 1 and enter its PIN. Choose transfer as a transaction type and you will see the window with accounts you can transfer the money from. **What was the expected outcome? ** the expected outcome was to display checking and savings as card one only has these valid accounts associated with it. Input: choose transfer transaction The state to bring the program to: you should have the window open that displays the account you can transfer money from. Expected output: Account to transfer from 1) Checking 2) savings What was the actual outcome? Account to transfer from 1) Checking 2) savings 3) Money Market | 2 | In Progress |  |  | 319555 | Rajpreet Gill | 319555 | Rajpreet Gill | Jan. 28, 2022 16:45 |  | 319555 | Rajpreet Gill | Jan. 28, 2022 16:48 | 0 | 0
3637290 | 68232 | ATM Project | 12 | ATM_1-12 | 292236 | Bug | 92350 | Version 1.1 | Withdraw function, incorrect withdrawal amount for input $200, for all accounts and cards | **The function being tested** Withdraw **The initial state of the system** System is on, serving a card, system is prompting the user to select to menu items an amount to withdraw **Steps to reproduce the defect/bug** 1) Insert a card 2) enter correct card number and PIN 3) Choose "Withdrawal" transaction 4) Choose account "Money Market" or "Checking" for Card 2 and/or "Checking" or "Saving" for Card 1 5) Choose amount of "$200" **What was the expected outcome?** System subtract $200 from balance of MMKT account from card 2 and an amount of $200 withdrawn. Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #2 WITHDRAWAL FROM: MMKT AMOUNT: $200.00 TOTAL BAL: $4600.00 AVAILABLE: $4600.00 **What was the actual outcome?** System subtract $20 from balance of of MMKT account from card 3 and an amount of $20 withdrawn. Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #2 WITHDRAWAL FROM: MMKT AMOUNT: $20.00 TOTAL BAL: $4780.00 AVAILABLE: $4780.00 | 2 | In Progress | 0 | Fixed | 319541 | LAB1-NHRL | 319541 | LAB1-NHRL | Jan. 20, 2022 16:38 |  | 319541 | LAB1-NHRL | Jan. 28, 2022 15:33 | 0 | 0 | Jan. 28, 2022 15:33 LAB1-NHRL The computational bugs have been fixed but the incorrect card number is still an issue.
3637287 | 68232 | ATM Project | 10 | ATM_1-10 | 292236 | Bug | 92350 | Version 1.1 | Withdraw function, incorrect withdrawal amount for input $60, for all accounts and cards | **The function being tested** Withdraw **The initial state of the system** System is on, serving a card, system is prompting the user to select to menu items an amount to withdraw **Steps to reproduce the defect/bug** 1) Insert a card 2) enter correct card number and PIN 3) Choose "Withdrawal" transaction 4) Choose account "Money Market" or "Checking" for Card 2 and/or "Checking" or "Saving" for Card 1 5) Choose amount of "$60" **What was the expected outcome?** System subtract $60 from balance of MMKT account from card 2 and an amount of $60 withdrawn. Thu Jan 20 14:57:18 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #3 WITHDRAWAL FROM: MMKT AMOUNT: $60.00 TOTAL BAL: $4840.00 AVAILABLE: $4840.00 **What was the actual outcome?** System subtract $100 from balance of of MMKT account from card 3 and an amount of $100 withdrawn. Thu Jan 20 14:57:18 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #3 WITHDRAWAL FROM: MMKT AMOUNT: $100.00 TOTAL BAL: $4800.00 AVAILABLE: $4800.00 | 2 | In Progress | 0 | Fixed | 319541 | LAB1-NHRL | 319541 | LAB1-NHRL | Jan. 20, 2022 16:30 |  | 319541 | LAB1-NHRL | Jan. 28, 2022 15:33 | 0 | 0 | Jan. 28, 2022 15:33 LAB1-NHRL The computational bugs have been fixed but the incorrect card number is still an issue.
3637266 | 68232 | ATM Project | 4 | ATM_1-4 | 292236 | Bug | 92350 | Version 1.1 | Withdraw function, incorrect withdrawal amount for input $40, for all accounts and cards | **The function being tested** Withdraw **The initial state of the system** System is on, serving a card, system is prompting the user to select to menu items an amount to withdraw **Steps to reproduce the defect/bug** 1) Insert a card 2) enter correct card number and PIN 3) Choose "Withdrawal" transaction 4) Choose account "Money Market" or "Checking" for Card 2 and/or "Checking" or "Saving" for Card 1 5) Choose amount of "$40" **What was the expected outcome?** System subtract $40 from balance of MMKT account from card 2 and an amount of $40 withdrawn. Thu Jan 20 14:55:56 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #2 WITHDRAWAL FROM: MMKT AMOUNT: $40.00 TOTAL BAL: $4920.00 AVAILABLE: $4920.00 **What was the actual outcome?** System subtract $60 from balance of of MMKT account from card 3 and an amount of $60 withdrawn. Thu Jan 20 14:55:56 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #2 WITHDRAWAL FROM: MMKT AMOUNT: $60.00 TOTAL BAL: $4900.00 AVAILABLE: $4900.00 | 2 | In Progress | 0 | Fixed | 319541 | LAB1-NHRL | 319541 | LAB1-NHRL | Jan. 20, 2022 16:11 |  | 319541 | LAB1-NHRL | Jan. 28, 2022 15:32 | 0 | 0 | Jan. 28, 2022 15:32 LAB1-NHRL The computational bugs have been fixed but the incorrect card number is still an issue.
3637254 | 68232 | ATM Project | 2 | ATM_1-2 | 292236 | Bug | 92350 | Version 1.1 | Withdraw function, incorrect withdrawal amount for input $20, for all accounts and cards | **The function being tested** Withdraw **The initial state of the system** System is on, serving a card, system is prompting the user to select to menu items an amount to withdraw **Steps to reproduce the defect/bug** 1) Insert a card 2) enter correct card number and PIN 3) Choose "Withdrawal" transaction 4) Choose account "Money Market" or "Checking" for Card 2 and/or "Checking" or "Saving" for Card 1 5) Choose amount of "$20" **What was the expected outcome?** System subtract $20 from balance of MMKT account from card 2 and an amount of $20 withdrawn. Thu Jan 20 14:55:00 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 WITHDRAWAL FROM: MMKT AMOUNT: $20.00 TOTAL BAL: $4980.00 AVAILABLE: $4980.00 **What was the actual outcome?** System subtract $40 from balance of MMKT account from card 3 and an amount of $40 withdrawn. Thu Jan 20 14:55:00 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #1 WITHDRAWAL FROM: MMKT AMOUNT: $40.00 TOTAL BAL: $4960.00 AVAILABLE: $4960.00 | 2 | In Progress | 0 | Fixed | 319541 | LAB1-NHRL | 319541 | LAB1-NHRL | Jan. 20, 2022 15:59 |  | 319541 | LAB1-NHRL | Jan. 28, 2022 15:32 | 0 | 0 | Jan. 28, 2022 15:32 LAB1-NHRL The computational bugs have been fixed but the incorrect card number is still an issue.
3637289 | 68232 | ATM Project | 11 | ATM_1-11 | 292236 | Bug | 92350 | Version 1.1 | Withdraw function, incorrect withdrawal amount for input $100, for all accounts and cards | **The function being tested** Withdraw **The initial state of the system** System is on, serving a card, system is prompting the user to select to menu items an amount to withdraw **Steps to reproduce the defect/bug** 1) Insert a card 2) enter correct card number and PIN 3) Choose "Withdrawal" transaction 4) Choose account "Money Market" or "Checking" for Card 2 and/or "Checking" or "Saving" for Card 1 5) Choose amount of "$100" **What was the expected outcome?** System subtract $100 from balance of MMKT account from card 2 and an amount of $100 withdrawn. Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 WITHDRAWAL FROM: MMKT AMOUNT: $100.00 TOTAL BAL: $4900.00 AVAILABLE: $4900.00 **What was the actual outcome?** System subtract $200 from balance of of MMKT account from card 3 and an amount of $200 withdrawn. Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #1 WITHDRAWAL FROM: MMKT AMOUNT: $200.00 TOTAL BAL: $4800.00 AVAILABLE: $4800.00 | 2 | In Progress | 0 | Fixed | 319541 | LAB1-NHRL | 319541 | LAB1-NHRL | Jan. 20, 2022 16:34 |  | 319541 | LAB1-NHRL | Jan. 28, 2022 15:31 | 0 | 0 | Jan. 28, 2022 15:31 LAB1-NHRL The computational bugs have been fixed but the incorrect card number is still an issue.
3640141 | 68232 | ATM Project | 18 | ATM_1-18 | 292236 | Bug | 92349 | Version 1.0 | MFT: Test Case 33 (System asks customer to choose an account to inquire about) | **The function being tested:** Inquiry **The initial state of the system:** Menu of transaction types is being displayed **Steps to reproduce the defect/bug:** Choose inquiry transaction **What was the expected outcome?** System displays a menu of account types For Card 1 expected: Checking and Savings For Card 2 expected: Checking and Money Market **What was the actual outcome?** Incorrect account types are displayed for Card 1 For Card 1 displayed: Checking and Money Market For Card 2 displayed: Checking and Money Market | 3 | Resolved | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 21, 2022 16:14 |  | 319553 | Huda Abbas | Jan. 28, 2022 15:04 | 0 | 0
3640133 | 68232 | ATM Project | 16 | ATM_1-16 | 292236 | Bug | 92349 | Version 1.0 | MFT Test Case#16: System verifies that customer's balance is sufficient to fulfill the request | **The function being tested:** System verifies that customer's balance is sufficient to fulfill the request **The initial state of the system:** System is requesting a withdrawal amount **Steps to reproduce the defect/bug:** Provide fifteen $20 bills to the ATM before inserting a card. Then insert card 1 and enter correct PIN. Select Withdrawl transaction. Then select Checking account to withdraw from. Choose $200 to withdraw from the account. **What was the expected outcome?** System displays an appropriate message and offers customer the option of choosing to do another transaction or not. **What was the actual outcome?** System does not display an appropriate message. It also shows a receipt. Menu Output: Wood you like to do another transaction? 1) Yes 2) No Receipt Output: Fri Jan 21 19:07:43 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 WITHDRAWAL FROM: CHKG AMOUNT: $20.00 TOTAL BAL: $80.00 AVAILABLE: $80.00 | 3 | Resolved | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 21, 2022 16:05 |  | 319560 | Lubaba Sheikh | Jan. 27, 2022 11:06 | 0 | 0
3637279 | 68232 | ATM Project | 8 | ATM_1-8 | 292236 | Bug | 92349 | Version 1.0 | Transaction Receipt with Incorrect Card Number | **The function being tested:** Receipt of each transaction **The initial state of the system:** The system is on the menu that displays the different transaction types **Steps to reproduce the defect/bug:** Insert card, enter a valid card number and it's PIN. Select Balance Inquiry, then select Checking ( or select any valid transaction that displays a reciept) **What was the expected outcome?** The system shows a receipt with the correct card number according to card that is logged in For Card 1: Thu Jan 20 16:09:41 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 1 TRANS #1 INQUIRY FROM: CHKG TOTAL BAL: $100.00 AVAILABLE: $100.00 For Card 2: Thu Jan 20 16:17:22 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #3 INQUIRY FROM: CHKG TOTAL BAL: $100.00 AVAILABLE: $100.00 **What was the actual outcome?** For Card 1: Thu Jan 20 16:09:41 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 INQUIRY FROM: CHKG TOTAL BAL: $100.00 AVAILABLE: $100.00 For Card 2: Thu Jan 20 16:17:22 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #3 INQUIRY FROM: CHKG TOTAL BAL: $100.00 AVAILABLE: $100.00 | 2 | In Progress | 0 | Fixed | 319560 | Lubaba Sheikh | 319560 | Lubaba Sheikh | Jan. 20, 2022 16:26 |  | 319560 | Lubaba Sheikh | Jan. 25, 2022 10:31 | 0 | 0 | Jan. 21, 2022 20:24 Lubaba Sheikh Defect still exists in version 1.1
3637259 | 68232 | ATM Project | 3 | ATM_1-3 | 292236 | Bug | 92349 | Version 1.0 | Deposit function for checkings account (MFT test case 22) | **The function being tested** Deposit - checkings account **The initial state of the system ** The system is prompting the user to deposit a specific amount of money in the checkings account. **Steps to reproduce the defect/bug** Insert a card, then enter the correct card number and PIN. Test the deposit function with the card using the checkings account. **What was the expected outcome? ** the expected outcome is to add the deposit value into the account balance. Input: checking account and $20 for the amount to deposit. The state to bring the program to: you should have the window open where it asks for you to deposit the amount of money you would like to deposit in the checking account. You may use card one or card two as this defect exists in both. Expected outcome: Thu Jan 20 14:34:27 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 1 TRANS #7 DEPOSIT TO: CHKG AMOUNT: $20.00 TOTAL BAL: $120.00 AVILABLE: $100.00 **What was the actual outcome?** the actual outcome adds an incorrect value (not the deposit value) to the account balance. It only adds $10 to the total balance even though it should add $20. As well, the number of the card being used is incorrectly displayed as it should display CARD 1 instead of CARD 2 as card #1 was being used for this transaction. Actual outcome: Thu Jan 20 14:34:27 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #7 DEPOSIT TO: CHKG AMOUNT: $20.00 TOTAL BAL: $110.00 AVILABLE: $100.00 | 2 | In Progress | 0 | Fixed | 319555 | Rajpreet Gill | 319555 | Rajpreet Gill | Jan. 20, 2022 16:05 |  | 319555 | Rajpreet Gill | Jan. 25, 2022 09:52 | 0 | 0 | Jan. 21, 2022 16:33 Rajpreet Gill Defect still exists in version 1.1
3640139 | 68232 | ATM Project | 17 | ATM_1-17 | 292236 | Bug | 92349 | Version 1.0 | Deposit into savings account using card one (MFT test case 22) | The function being tested Deposit - savings account using card one **The initial state of the system ** The system is prompting the user to deposit a specific amount of money in the savings account. Steps to reproduce the defect/bug Insert a card, then enter the correct card number and PIN. Test the deposit function with the card using the savings account. **What was the expected outcome? ** the expected outcome is to add the deposit value into the account balance. Input: using card one, savings account to deposit $20 in this account The state to bring the program to: you should have the window open where it asks for you to deposit the amount of money you would like to deposit in the savings account using card one. Expected output: Fri Jan 21 16:07:49 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 1 TRANS #8 DEPOSIT TO: SVGS AMOUNT: $20.00 TOTAL BAL: $1020.00 AVILABLE: $1000.00 What was the actual outcome? the actual outcome adds an incorrect value (not the deposit value) to the account balance. It only adds $10 to the total balance even though it should add $20. As well, the number of the card being used is incorrectly displayed as it should display CARD 1 instead of CARD 2 as card #1 was being used for this transaction. Fri Jan 21 16:07:49 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 DEPOSIT TO: SVGS AMOUNT: $20.00 TOTAL BAL: $1010.00 AVAILABLE: $1000.00 | 2 | In Progress | 0 | Fixed | 319555 | Rajpreet Gill | 319555 | Rajpreet Gill | Jan. 21, 2022 16:10 |  | 319555 | Rajpreet Gill | Jan. 25, 2022 09:51 | 0 | 0 | Jan. 21, 2022 16:28 Rajpreet Gill Defect still exists in version 1.1
3637281 | 68232 | ATM Project | 9 | ATM_1-9 | 292236 | Bug | 92349 | Version 1.0 | Deposit function for money market using card two (MFT test case 22) | The function being tested Deposit - money market account using card two **The initial state of the system ** The system is prompting the user to deposit a specific amount of money in the money market account using card two. Steps to reproduce the defect/bug Insert a card, then enter the correct card number and PIN. Test the deposit function with card two using the money market account. **What was the expected outcome? ** the expected outcome is to add the deposit value into the account balance. Input: using card two to deposit $20 into the money market account. The state to bring the program to: you should have the window open where it asks for you to deposit the amount of money you would like to deposit in the money market account using card two. Expected output: Thu Jan 20 14:59:56 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #8 DEPOSIT TO: MMKT AMOUNT: $20.00 TOTAL BAL: $5020.00 AVILABLE: $5000.00 What was the actual outcome? the actual outcome adds an incorrect value (not the deposit value) to the account balance. It adds $10 less from the deposit value to the total balance. As well, the number of the card being used is incorrectly displayed as it should display CARD 3 instead of CARD 2 as card #2 was being used for this transaction. Actual outcome: Thu Jan 20 14:59:56 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #6 DEPOSIT TO: MMKT AMOUNT: $20.00 TOTAL BAL: $5010.00 AVILABLE: $5000.00 | 2 | In Progress | 0 | Fixed | 319555 | Rajpreet Gill | 319555 | Rajpreet Gill | Jan. 20, 2022 16:26 |  | 319555 | Rajpreet Gill | Jan. 25, 2022 09:50 | 0 | 0 | Jan. 21, 2022 16:27 Rajpreet Gill Defect still exists in version 1.1
3640155 | 68232 | ATM Project | 20 | ATM_1-20 | 292236 | Bug | 92349 | Version 1.0 | MFT: Test Case 40 (Correct re-entry of PIN on the third try is accepted) | **The function being tested:** Invalid PIN Extension **The initial state of the system:** Request to re-enter PIN is being displayed **Steps to reproduce the defect/bug**: Enter incorrect PIN the first time and second times, then correct PIN the third time **What was the expected outcome?** Original transaction completes successfully **What was the actual outcome?** System again requests user to enter a valid PIN. | 2 | In Progress | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 21, 2022 16:42 |  | 319553 | Huda Abbas | Jan. 21, 2022 20:38 | 0 | 0 | Jan. 21, 2022 20:38 Huda Abbas Defect still exists in version 1.1
3640112 | 68232 | ATM Project | 15 | ATM_1-15 | 292236 | Bug | 92349 | Version 1.0 | MFT: Test Case 34 (System performs a legitimate inquiry transaction properly) | **The function being tested:** Inquiry **The initial state of the system:** System is displaying menu of account types **Steps to reproduce the defect/bug:** Choose checking account **What was the expected outcome?** System prints a correct receipt showing correct balance; System records transaction correctly in the log (showing both message to the bank and approval back) **What was the actual outcome?** Correct balance is printed, but incorrect card number. Fri Jan 21 15:37:37 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 3 TRANS #6 INQUIRY FROM: CHKG TOTAL BAL: $100.00 AVAILABLE: $100.00 Transaction is also recorded in the log. Message: INQUIRY CARD# 2 TRANS# 6 FROM 0 NO TO NO AMOUNT Response: SUCCESS | 2 | In Progress | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 21, 2022 15:22 |  | 319553 | Huda Abbas | Jan. 21, 2022 20:37 | 0 | 0 | Jan. 21, 2022 20:37 Huda Abbas Defect still exists in version 1.1
3637246 | 68232 | ATM Project | 1 | ATM_1-1 | 292236 | Bug | 92349 | Version 1.0 | Transfers correct amount for all accounts and cards | **The function being tested:** Transfer **The initial state of the system:** System is displaying a request for the customer to type a dollar amount **Steps to reproduce the defect/bug**: Insert a card, then enter correct card number and PIN. Select 3 on the menu of transaction types to begin your transfer. Select two valid account types with a sufficient balance and enter a legitimate dollar amount. **What was the expected outcome?** The system correctly prints a receipt showing amount and correct updated balance. System records transaction correctly in the log. Expected receipt example as follows: Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 1 TRANS #1 TRANSFER FROM: CHKG TO: SVGS AMOUNT: $20.59 TOTAL BAL: $1020.59 AVAILABLE: $1020.59 **What was the actual outcome?** The system incorrectly printed the receipt with the wrong card number. Additionally the accounts transferred from and to has been swapped and the amount inputted is off by $0.50 so the updated balance is also incorrect. Actual receipt example as follows: Thu Jan 20 15:00:36 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #1 TRANSFER FROM: SVGS TO: CHKG AMOUNT: $20.09 TOTAL BAL: $1020.09 AVAILABLE: $1020.09 | 2 | In Progress | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 20, 2022 15:44 |  | 319553 | Huda Abbas | Jan. 21, 2022 20:34 | 0 | 0 | Jan. 21, 2022 17:06 Huda Abbas Found bug again from MFT Test Case 29
3640153 | 68232 | ATM Project | 19 | ATM_1-19 | 292236 | Bug | 92349 | Version 1.0 | MFT: Test Case 39 (Correct re-entry of PIN on the second try is accepted) | **The function being tested:** Invalid PIN Extension **The initial state of the system:** Request to re-enter PIN is being displayed **Steps to reproduce the defect/bug**: Enter incorrect PIN the first time, then correct PIN the second time **What was the expected outcome?** Original transaction completes successfully **What was the actual outcome?** System again requests user to enter a valid PIN. | 2 | In Progress | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 21, 2022 16:40 |  | 319553 | Huda Abbas | Jan. 21, 2022 20:32 | 0 | 0 | Jan. 21, 2022 20:32 Huda Abbas Defect still exists in version 1.1
3637278 | 68232 | ATM Project | 7 | ATM_1-7 | 292236 | Bug | 92349 | Version 1.0 | Retrying PIN after entering invalid PIN once | **The function being tested:** Invalid PIN **The initial state of the system:** System is displaying a re-request for the customer to enter the PIN for their credit card **Steps to reproduce the defect/bug**: Click to insert a card, then enter correct card number. At first enter incorrect PIN number then try again a second time and enter correct PIN number for the respective card added. **What was the expected outcome?** PIN entered successfully and menu of transaction types is being displayed. **What was the actual outcome?** System again requests user to re-enter a valid PIN. Example output for Card 1 after valid PIN of 42 is inputted: "Please enter your PIN then press ENTER" | 2 | In Progress | 0 | Fixed | 319553 | Huda Abbas | 319553 | Huda Abbas | Jan. 20, 2022 16:24 |  | 319553 | Huda Abbas | Jan. 21, 2022 20:30 | 0 | 0 | Jan. 21, 2022 17:05 Huda Abbas Found again in MFT Test Case 37 | Jan. 21, 2022 20:30 Huda Abbas Defect still present in Version 1.1